## Tasks
Task ID | Task Name | Bucket Name | Progress | Priority | Assigned To | Created By | Created Date | Start date | Due date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels
-7xpm3YShkuLUM9rglD3lMkANT-8 | Member 2 Proposal Draft Report | Report Writing | Completed | Medium | MARK J J it22328120 | SANDAMINI G H D H it22291882 | 2025-08-08 |  | 08/29/2025 | false | false | 08/29/2025 | MARK J J it22328120 |  |  | Cranberry
2mUChCTiM0qtO-A5uOylgckAMlC_ | Member 4 Thesis Draft Report | Report Writing | Completed | Important | SANDAMINI G H D H it22291882 | NETHMI G.K. it22546166 | 2025-08-08 | 04/20/2026 | 04/26/2026 | false | false | 04/30/2026 | SANDAMINI G H D H it22291882 |  |  | Aqua
37qLaWJXrk6tHjZLBWT3wMkAG8h9 | Final Presentation Slide Creation | Presentation Preparation | In progress | Important | FARSITH M F M it22354556;MARK J J it22328120;NETHMI G.K. it22546166;SANDAMINI G H D H it22291882 | MARK J J it22328120 | 2025-08-08 | 05/01/2026 | 05/04/2026 | false | false
3ewXxuP6uUuhrkzleYO0zckAHBFH | Member 1 Thesis Draft Report | Report Writing | Completed | Important | FARSITH M F M it22354556 | NETHMI G.K. it22546166 | 2025-08-08 | 04/20/2026 | 04/26/2026 | false | false | 04/30/2026 | FARSITH M F M it22354556 |  |  | Aqua
4xflG9K_f0-tnRnDM-VDEskAGVwb | TAF Document Creation | Report Writing | Completed | Important | FARSITH M F M it22354556;MARK J J it22328120;NETHMI G.K. it22546166;SANDAMINI G H D H it22291882 | SANDAMINI G H D H it22291882 | 2025-08-08 |  | 08/29/2025 | false | false | 2025-08-30 | NETHMI G.K. it22546166
5vJeKYxlZUGnsQ8qhX2ER8kAP5Nu | Train models | Model Development | Completed | Urgent | NETHMI G.K. it22546166;FARSITH M F M it22354556;MARK J J it22328120;SANDAMINI G H D H it22291882 | NETHMI G.K. it22546166 | 2025-08-08 | 08/31/2025 | 02/28/2026 | false | false | 04/30/2026 | FARSITH M F M it22354556 | 4/4 | Member 4;Member 2;Member 1;Member 3
663_Xy3fLk6SWLcLMsiIeckADi1O | Create timeline | Project Planning | Completed | Medium | FARSITH M F M it22354556;MARK J J it22328120;NETHMI G.K. it22546166;SANDAMINI G H D H it22291882 | FARSITH M F M it22354556 | 2025-08-08 |  | 08/07/2025 | false | false | 08/07/2025 | NETHMI G.K. it22546166
93VkZ-KAPEm2bO0E15PcRMkABhoB | Prepare references | Research & Literature Review | Completed | Important | NETHMI G.K. it22546166;FARSITH M F M it22354556;MARK J J it22328120;SANDAMINI G H D H it22291882 | NETHMI G.K. it22546166 | 2025-08-08 |  | 08/18/2025 | false | false | 08/18/2025 | NETHMI G.K. it22546166 | 4/4 | Member 2;Member 3;Member 1;Member 4
964pmgUHG0iL2aOogHj-4skACnwU | Perform model testing | Testing & Evaluation | Completed | Important | NETHMI G.K. it22546166;FARSITH M F M it22354556;MARK J J it22328120 | NETHMI G.K. it22546166 | 2025-08-08 | 04/20/2026 | 04/30/2026 | false | false | 04/30/2026 | NETHMI G.K. it22546166
Bb0eW_9H2EqogmPFTGCvxckAI4zW | Member 3 Final Thesis Report | Report Writing | In progress | Urgent | NETHMI G.K. it22546166 | SANDAMINI G H D H it22291882 | 2025-08-08 | 04/30/2026 | 05/13/2026 | false | false |  |  |  |  | Lime
D6xmpEqzjECSrplBcyLYbskAOd7U | Collect research papers | Research & Literature Review | Completed | Important | NETHMI G.K. it22546166;FARSITH M F M it22354556;MARK J J it22328120;SANDAMINI G H D H it22291882 | NETHMI G.K. it22546166 | 2025-08-08 |  | 08/10/2025 | false | false | 08/10/2025 | NETHMI G.K. it22546166 | 4/4 | Member 3;Member 1;Member 4;Member 2
DLMMYO0-o0ybhgQ-4mhLeckAC_rl | Integrate Firebase database | Development | Completed | Important | NETHMI G.K. it22546166;FARSITH M F M it22354556;MARK J J it22328120;SANDAMINI G H D H it22291882 | MARK J J it22328120 | 2025-08-08 |  | 04/25/2026 | false | false | 04/30/2026 | NETHMI G.K. it22546166
Dkb07UtNTEmXVL9-addjhMkAFf6G | Member 1 Final Thesis Report | Report Writing | In progress | Urgent | FARSITH M F M it22354556 | NETHMI G.K. it22546166 | 2025-08-08 | 04/30/2026 | 05/13/2026 | false | false |  |  |  |  | Lime
G9hv2_7YykS4faRchjxOGskAPWUw | Member 2 Final Thesis Report | Report Writing | In progress | Urgent | MARK J J it22328120 | NETHMI G.K. it22546166 | 2025-08-08 | 04/30/2026 | 05/13/2026 | false | false | 04/30/2026 |  |  |  | Lime
IRTeH3iss0iDXuzI9X6dkskAOzHI | Develop backend (Flask APIs) | Development | Completed | Important | NETHMI G.K. it22546166;FARSITH M F M it22354556;MARK J J it22328120;SANDAMINI G H D H it22291882 | NETHMI G.K. it22546166 | 2025-08-08 | 09/02/2025 | 04/20/2026 | false | false | 09/02/2025 | NETHMI G.K. it22546166 | 4/4 | Member 1;Member 4;Member 3;Member 2
JF1wCsgzZkqBazcVjAfVn8kAH8xq | Identify research gap | Research & Literature Review | Completed | Important | NETHMI G.K. it22546166;FARSITH M F M it22354556;MARK J J it22328120;SANDAMINI G H D H it22291882 | NETHMI G.K. it22546166 | 2025-08-08 |  | 08/15/2025 | false | false | 04/30/2026 | NETHMI G.K. it22546166 | 4/4 | Member 1;Member 2;Member 3;Member 4
Jbq5imGB-ESagiNqH4Y9tMkABH6v | Member 1 Proposal Draft Report | Report Writing | Completed | Medium | FARSITH M F M it22354556 | FARSITH M F M it22354556 | 2025-08-08 |  | 08/29/2025 | false | false | 04/30/2026 | FARSITH M F M it22354556 |  |  | Cranberry
Lp9io1Oy4ESytv1pxLCQ28kAFodv | Member 4 Proposal Final Report | Report Writing | Completed | Medium | SANDAMINI G H D H it22291882 | NETHMI G.K. it22546166 | 2025-08-08 |  | 09/19/2026 | false | false | 04/30/2026 | SANDAMINI G H D H it22291882 |  |  | Orange
MARlEGQ4PU6dYCHapa9zzskACo4_ | PP2 Presentation Slide Creation | Presentation Preparation | Completed | Medium | FARSITH M F M it22354556;MARK J J it22328120;NETHMI G.K. it22546166;SANDAMINI G H D H it22291882 | NETHMI G.K. it22546166 | 2025-08-08 |  | 03/08/2026 | false | false | 04/30/2026 | NETHMI G.K. it22546166
MTUk0jLhg0ep5iJET8JtUMkAAsHb | Develop frontend (React + Vite) | Development | Completed | Important | NETHMI G.K. it22546166;FARSITH M F M it22354556;MARK J J it22328120;SANDAMINI G H D H it22291882 | SANDAMINI G H D H it22291882 | 2025-08-08 | 09/02/2025 | 04/20/2026 | false | false | 09/02/2025 | NETHMI G.K. it22546166 | 4/4 | Member 1;Member 4;Member 2;Member 3
NBWC2_F8fES6Hqn2t2u298kAJUGr | Member 4 Final Thesis Report | Report Writing | In progress | Urgent | SANDAMINI G H D H it22291882 | NETHMI G.K. it22546166 | 2025-08-08 | 04/30/2026 | 05/13/2026 | false | false |  |  |  |  | Lime
O26HgQYipE2CkdYqCBEBQMkAI6XL | Member 4 Proposal Draft Report | Report Writing | Completed | Medium | SANDAMINI G H D H it22291882 | NETHMI G.K. it22546166 | 2025-08-08 |  | 08/29/2025 | false | false | 04/30/2026 | SANDAMINI G H D H it22291882 |  |  | Cranberry
QzbRPKlF9Eia3lioQToTAMkAOU0E | Validate prediction module | Testing & Evaluation | Completed | Important | NETHMI G.K. it22546166;FARSITH M F M it22354556;MARK J J it22328120;SANDAMINI G H D H it22291882 | NETHMI G.K. it22546166 | 2025-08-08 | 04/20/2026 | 04/30/2026 | false | false | 04/30/2026 | NETHMI G.K. it22546166
T6qAcMi4w06WpDvd7zrxgskABfYN | Integration testing | Testing & Evaluation | Completed | Important | NETHMI G.K. it22546166;FARSITH M F M it22354556;MARK J J it22328120;SANDAMINI G H D H it22291882 | NETHMI G.K. it22546166 | 2025-08-08 | 04/20/2026 | 04/30/2026 | false | false | 04/30/2026 | NETHMI G.K. it22546166
TBye3wdl5Eqcg1_6okvrxMkAErFm | Member 3 Proposal Final Report | Report Writing | Completed | Medium | NETHMI G.K. it22546166 | NETHMI G.K. it22546166 | 2025-08-08 |  | 09/19/2025 | false | false | 04/30/2026 | NETHMI G.K. it22546166 |  |  | Orange
TqacBlfPYU2ol4TJymSa9MkAJ2BX | Research Paper publication evidence submission | Report Writing | Not started | Urgent |  | NETHMI G.K. it22546166 | 2025-08-08 | 04/20/2026 | 06/15/2026 | false | false
WWtq-7iibUSsdPTyHJbrg8kAHvQi | Evaluate model performance | Model Development | Completed | Urgent | FARSITH M F M it22354556;MARK J J it22328120;NETHMI G.K. it22546166;SANDAMINI G H D H it22291882 | MARK J J it22328120 | 2025-08-08 | 02/28/2026 | 03/01/2026 | false | false | 04/30/2026 | FARSITH M F M it22354556 | 4/4 | Member 3;Member 4;Member 1;Member 2
_3jvEBl1pk-UeTEDPH7IvckAHG0A | PP1 Presentation Slide Creation | Presentation Preparation | Completed | Medium | FARSITH M F M it22354556;MARK J J it22328120;NETHMI G.K. it22546166;SANDAMINI G H D H it22291882 | NETHMI G.K. it22546166 | 2025-08-08 |  | 01/06/2026 | false | false | 04/30/2026 | NETHMI G.K. it22546166
azU32WZK1kS_RRByezh64ckAGYW2 | Member 3 Proposal Draft Report | Report Writing | Completed | Medium | NETHMI G.K. it22546166 | NETHMI G.K. it22546166 | 2025-08-08 |  | 08/29/2025 | false | false | 04/30/2026 | NETHMI G.K. it22546166 |  |  | Cranberry
e9ZeA2RlT0m--L-ihGzHlMkANZrc | Member 2 Thesis Draft Report | Report Writing | Completed | Important | MARK J J it22328120 | FARSITH M F M it22354556 | 2025-08-08 | 04/20/2026 | 04/26/2026 | false | false | 04/30/2026 | MARK J J it22328120 |  |  | Aqua
fhwIXqsEskKr3UdXvghEGckAOGTe | Design system architecture | System Design | Completed | Important | FARSITH M F M it22354556;MARK J J it22328120 | SANDAMINI G H D H it22291882 | 2025-08-08 |  | 08/20/2025 | false | false | 04/30/2026 | FARSITH M F M it22354556
jx-UqO1M9EyrM_gQVfcyp8kABPlr | Member 1 Proposal Final Report | Report Writing | Completed | Medium | FARSITH M F M it22354556 | NETHMI G.K. it22546166 | 2025-08-08 |  | 09/19/2025 | false | false | 04/30/2026 | FARSITH M F M it22354556 |  |  | Orange
k1Bk3vkvEkuVvWGVXUguqckAGAbC | Define modules | System Design | Completed | Important | NETHMI G.K. it22546166;FARSITH M F M it22354556;MARK J J it22328120;SANDAMINI G H D H it22291882 | NETHMI G.K. it22546166 | 2025-08-08 |  | 08/22/2025 | false | false | 04/30/2026 | NETHMI G.K. it22546166
lvwcKdgzZ0i6g1imE5S8I8kAL1Nc | Define project scope | Project Planning | Completed | Medium | FARSITH M F M it22354556;MARK J J it22328120;NETHMI G.K. it22546166;SANDAMINI G H D H it22291882 | MARK J J it22328120 | 2025-08-08 |  | 08/02/2025 | false | false | 04/30/2026 | NETHMI G.K. it22546166
m-BDNicfxEGzGydgBe6wpckAMHGH | Assign team roles | Project Planning | Completed | Medium | FARSITH M F M it22354556;MARK J J it22328120 | NETHMI G.K. it22546166 | 2025-08-08 |  | 08/06/2025 | false | false | 04/30/2026 | FARSITH M F M it22354556
mrsqJVdoU027hCrPnKbMlMkAH5Za | Proposal Presentation Slide Creation | Presentation Preparation | Completed | Medium | FARSITH M F M it22354556;MARK J J it22328120;NETHMI G.K. it22546166;SANDAMINI G H D H it22291882 | NETHMI G.K. it22546166 | 2025-08-08 |  | 09/07/2025 | false | false | 04/30/2026 | NETHMI G.K. it22546166
opQJ084wUE2EVimrdGLaeskAMbwA | Preprocess dataset | Model Development | Completed | Urgent | NETHMI G.K. it22546166;FARSITH M F M it22354556;MARK J J it22328120;SANDAMINI G H D H it22291882 | SANDAMINI G H D H it22291882 | 2025-08-08 |  | 08/31/2025 | false | false | 04/30/2026 | FARSITH M F M it22354556 | 4/4 | Member 3;Member 4;Member 2;Member 1
pJCB9HgW-kaJQdFHZE_CBskAHsef | Perform functional testing | Testing & Evaluation | Completed | Important | NETHMI G.K. it22546166;FARSITH M F M it22354556;MARK J J it22328120;SANDAMINI G H D H it22291882 | NETHMI G.K. it22546166 | 2025-08-08 | 04/20/2026 | 04/30/2026 | false | false | 04/30/2026 | NETHMI G.K. it22546166
syJ7Dqvgw0ih77nbdtpOyskANJLi | Collect datasets | Model Development | Completed | Urgent | NETHMI G.K. it22546166;FARSITH M F M it22354556;MARK J J it22328120;SANDAMINI G H D H it22291882 | NETHMI G.K. it22546166 | 2025-08-08 |  | 08/22/2025 | false | false | 04/30/2026 | MARK J J it22328120 | 4/4 | Member 2;Member 3;Member 1;Member 4
vnv8z2WAO0mXJfsQWJVLIskAFdQ5 | Member 2 Proposal Final Report | Report Writing | Completed | Medium | MARK J J it22328120 | FARSITH M F M it22354556 | 2025-08-08 |  | 09/19/2025 | false | false | 04/30/2026 | MARK J J it22328120 |  |  | Orange
vwR8A6MY_Ue0amdBWWcuH8kADEEb | Create workflow diagrams | System Design | Completed | Important | NETHMI G.K. it22546166;SANDAMINI G H D H it22291882;FARSITH M F M it22354556 | NETHMI G.K. it22546166 | 2025-08-08 |  | 08/21/2025 | false | false | 04/30/2026 | NETHMI G.K. it22546166
wab1Hud7_0qfYT7bDVRnsckAAwNV | Research Paper writing | Report Writing | In progress | Urgent | MARK J J it22328120;FARSITH M F M it22354556;SANDAMINI G H D H it22291882;NETHMI G.K. it22546166 | NETHMI G.K. it22546166 | 2025-08-08 | 04/20/2026 | 05/08/2026 | false | false
xSn_PtrRlkyOStuWm6tfYskAKkB2 | Member 3 Thesis Draft Report | Report Writing | Completed | Important | NETHMI G.K. it22546166 | MARK J J it22328120 | 2025-08-08 | 04/20/2026 | 04/26/2026 | false | false | 04/30/2026 | NETHMI G.K. it22546166 |  |  | Aqua

## Plan name
Plan name | SignSight – Research Project Plan (PP2)
Plan ID | O_2E8ptql0iRlSvX6D_gn8kAGkLy
Date of export | 04/30/2026